## Status Report
Project Name | Werewolf Mafia |  | Date |  | Feb 3rd, 2024 | Project Manager |  | Sam Wald
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
Our team has been formed, roles are assigned, and we have set aside a regular time to meet twice weekly (with plans to reduce that time when it becomes unecessary). |  |  |  | Org chart |  | 100% | Complete
|  |  |  | Team Role definitions |  | 100% | Complete
|  |  |  | Meeting schedules |  | 100% | Complete
|  |  |  | Decide on Project Tracking tool |  | 100% | Complete
|  |  |  | Gantt Chart |  | 60% | On Track
|  |  |  | Determine Project Requirements |  | 0% | Future Task
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
Initial Team Meeting; Org chart creation; Gantt chart creation and permissions; class readings; |  |  | N/A |  |  | Future Meetings; Gantt Chart; Project requirements
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Sam Wald | Project Manager | 4 | Risk | Undetermined
Logan Tailleur | Chief Architect | 4
Calvin Pugmire | Front-End Engineer | 5
Hunter Larson | QA Engineer | 5 | Issue | Undetermined
Ethan Kerr | UI Designer | 2
Abel Nelson | Back-End Engineer | 3
Total |  | 23

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task