## Status Report
Project Name | Werewolf Mafia |  | Date |  | Feb 10th, 2024 | Project Manager |  | Sam Wald
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
Our team has solidified our vision for the project and have completed a requirements doc we are all satisfied with. We will begin the next phase of our research, |  |  |  | Determine Project Requirements |  | 100% | Complete
|  |  |  | Werewolf Game Functionality research |  | 0% | Future Task
|  |  |  | Architectural design |  | 20% | On Track
|  |  |  | QA setup for future testing |  | 50% | On Track
|  |  |  | PERT chart |  | 0% | Future Task
|  |  |  | Gantt chart |  | 30% | On Track
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
Team Meetings; Requirements doc; Wire-framing; Initial Architecture research; QA research; class readings; |  |  | N/A |  |  | Werewolf Game Functionality research; PERT chart; Gantt chart
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Sam Wald | Project Manager | 5 | Risk | Potential conlficts with QA and dev on git, we are exploring how we want to manage branches
Logan Tailleur | Chief Architect | 5
Calvin Pugmire | Front-End Engineer | 5
Hunter Larson | QA Engineer | 5
Ethan Kerr | UI Designer | 5
Abel Nelson | Back-End Engineer | 5
Total |  | 30

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task