## Status Report
Project Name | Werewolf Mafia |  | Date |  | Feb 17th, 2024 | Project Manager |  | Sam Wald
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
Our team has completed the PERT and Gantt charts, so we now have a good vision of what needs to happen, when it needs to happen by, and who's going to make it happen.
|  |  |  | Werewolf Game Functionality research |  | 100% | Complete
|  |  |  | Architectural diagram |  | 100% | Complete
|  |  |  | QA setup for future testing |  | 70% | On Track
|  |  |  | PERT chart |  | 100% | Complete
|  |  |  | Gantt chart |  | 100% | Complete
|  |  |  | Wireframe UI |  | 30% | On Track
|  |  |  | Database setup |  | 10% | On Track
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
Team Meetings; PERT Chart; Gantt Chart; Game functionality research; Wire-framing; assigning role UI; Architecture diagram; Test Environment Setup; Class Readings; |  |  | N/A |  |  | Wireframe; Initial Javascript game logic; Database set-up
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Sam Wald | Project Manager | 6 | Risk | The time required to achieve what we want for Demo 1 may be too much. We will keep an eye on things and re-evaluate at our next team meeting.
Logan Tailleur | Chief Architect | 5
Calvin Pugmire | Front-End Engineer | 6
Hunter Larson | QA Engineer | 5
Ethan Kerr | UI Designer | 5.3
Abel Nelson | Back-End Engineer | 5
Total |  | 32.3

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task