## Status Report
Project Name | Werewolf Mafia |  | Date |  | Feb 24th, 2024 | Project Manager |  | Sam Wald
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
Our team has completed the Architexture & Design documents, Database setup, and Front-end preparatory to Demo 1. We are now looking at connecting front-end and back-end, as well as finishing and testing logic for both. QA has been keeping things on track.
|  |  |  | Architectural diagram |  | 100% | Complete
|  |  |  | QA setup for future testing |  | 90% | On Track
|  |  |  | Front end for Demo 1 |  | 100% | Complete
|  |  |  | Javascript Research |  | 80% | On Track
|  |  |  | Wireframe UI |  | 100% | Complete
|  |  |  | Database setup & Connectivity |  | 70% | On Track
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
Team Meetings; Wire-framing; UI Development; Database connectivity; Database Logic; JavaScript Research; Architecture & Design doc; Class Readings; QA testing; QA automation setup |  |  | N/A |  |  | Full connectivity of front+back ends; QA testing of Demo 1; Demo 1 presentation
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Sam Wald | Project Manager | 5 | Risk
Logan Tailleur | Chief Architect | 5
Calvin Pugmire | Front-End Engineer | 8
Hunter Larson | QA Engineer | 6
Ethan Kerr | UI Designer | 5
Abel Nelson | Back-End Engineer | 5
Total |  | 34

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task