## Status Report
Project Name | Werewolf Mafia |  | Date |  | Mar 2nd, 2024 | Project Manager |  | Sam Wald
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
Our team has completed Demo 1. We will present Monday and wiill look for feedback from the presentation. At our Tuesday meeting we will evaluate feedback and determine where to go for demo #2. |  |  |  | Demo #1 Code |  | 100% | Complete
|  |  |  | Demo #1 Testing |  | 100% | Complete
|  |  |  | Demo #1 Video |  | 100% | Complete
|  |  |  | Database setup & Connectivity |  | 100% | Complete
|  |  |  | Feedback Evaluation |  | 0% | Future Task
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
Team Meetings; UI Development; Database connectivity; Database Logic; Class Readings; QA setup; QA testing; Demo #1 coding; Demo #1 testing; Demo #1 video |  |  | N/A |  |  | Demo 1 presentation; Feedback evaluation for Demo 2;
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Sam Wald | Project Manager | 5 | Risk | Everyone hates what we've done for Demo #1 :(
Logan Tailleur | Chief Architect | 5
Calvin Pugmire | Front-End Engineer | 7
Hunter Larson | QA Engineer | 6
Ethan Kerr | UI Designer | 5
Abel Nelson | Back-End Engineer | 6
Total |  | 34

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task