## Status Report
Project Name | Werewolf Mafia |  | Date |  | Mar 9th, 2024 | Project Manager |  | Sam Wald
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
Our team has completed and presented Demo 1. We are now beginning the next steps for demo #2. |  |  |  | Phase 2 UI |  | 30% | On Track
|  |  |  | Phase 2 Architecture |  | 60% | On Track
|  |  |  | Automation testing |  | 50% | On Track
|  |  |  | Phase 2 Database setup |  | 30% | On Track
|  |  |  | Feedback Evaluation |  | 100% | Complete
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
Team Meetings; UI Development; Database design; Phase #2 Architecture; Class Readings; QA testing; Automation testing; Demo #2 coding; |  |  | N/A |  |  | Phase 2 UI, database, and testing
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Sam Wald | Project Manager | 4 | Risk
Logan Tailleur | Chief Architect | 4
Calvin Pugmire | Front-End Engineer | 9.5
Hunter Larson | QA Engineer | 6
Ethan Kerr | UI Designer | 4
Abel Nelson | Back-End Engineer | 3
Total |  | 30.5

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task