## Status Report
Project Name | Werewolf Mafia |  | Date |  | Mar 16th, 2024 | Project Manager |  | Sam Wald
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
We are continuing development of phase 2 work. Ethan was out of the country this week and thus has 0 billable hours. |  |  |  | Phase 2 UI Code |  | 60% | On Track
|  |  |  | Phase 2 Architecture |  | 80% | On Track
|  |  |  | Phase 2 Database Code |  | 70% | On Track
|  |  |  | QA Testing |  | 60% | On Track
|  |  |  | Code Review |  | 100% | Complete
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
Team Meetings; Phase #2 Architecture; HTTP fetch requests and express routers; Database functions; Class Readings; QA manual testing; Automation testing; Phase #2 coding; Code reviews; |  |  | N/A |  |  | Phase 2 UI, database, and testing
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Sam Wald | Project Manager | 4 | Risk
Logan Tailleur | Chief Architect | 5
Calvin Pugmire | Front-End Engineer | 3.5
Hunter Larson | QA Engineer | 6
Ethan Kerr | UI Designer | 0
Abel Nelson | Back-End Engineer | 5
Total |  | 23.5

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task