## Status Report
Project Name | Werewolf Mafia |  | Date |  | Mar 23rd, 2024 | Project Manager |  | Sam Wald
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
We are nearly complete with Phase #2 and will make the finishing touches before demoing this Monday. Some QA testing will be pushed past to Tuesday. |  |  |  | Phase 2 UI Code |  | 90% | On Track
|  |  |  | Phase 2 Architecture |  | 90% | On Track
|  |  |  | Phase 2 Database Code |  | 90% | On Track
|  |  |  | QA Testing |  | 80% | Delayed
|  |  |  | Code Review |  | 100% | Complete
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
Team Meetings; Phase #2 HTML; Midterm Prep; Class Readings; Database functions; QA manual testing; Phase #2 coding; |  |  | QA Testing of phase #2 |  |  | Demo #2; Demo #2 feedback
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Sam Wald | Project Manager | 3 | Risk
Logan Tailleur | Chief Architect | 5
Calvin Pugmire | Front-End Engineer | 12.5
Hunter Larson | QA Engineer | 5
Ethan Kerr | UI Designer | 5
Abel Nelson | Back-End Engineer | 4
Total |  | 34.5

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task