## Status Report
Project Name | Werewolf Mafia |  | Date |  | Mar 30th, 2024 | Project Manager |  | Sam Wald
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
We have completed Phase #2 and are now pushing heavily with QA testing and app polishing. |  |  |  | Phase 2 UI Code |  | 100% | On Track
|  |  |  | Phase 2 Architecture |  | 100% | On Track
|  |  |  | Phase 2 Database Code |  | 100% | On Track
|  |  |  | QA Testing |  | 80% | Delayed
|  |  |  | Group QA testing |  | 80% | On Track
|  |  |  | Midterm prep |  | 90% | On Track
|  |  |  | Midterm |  | 0% | Future Task
[6 empty] | 0% | Future Task
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
Team Meetings; Phase #2 Demo; Midterm Prep; Class Readings; Database functions; QA manual testing; QA group testing Phase #2 coding and UI development; |  |  | QA Testing of phase #2 |  |  | Midterm!
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Sam Wald | Project Manager | 4 | Risk
Logan Tailleur | Chief Architect | 8
Calvin Pugmire | Front-End Engineer | 12
Hunter Larson | QA Engineer | 6
Ethan Kerr | UI Designer | 4
Abel Nelson | Back-End Engineer | 6
Total |  | 40

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task