## Status Report
Project Name | Werewolf Mafia |  | Date |  | April 13th, 2024 | Project Manager |  | Sam Wald
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
We have completed phase 3 and are ready to show off Demo 3! |  |  |  | Phase 3 UI Code |  | 100% | On Track
|  |  |  | Phase 3 Architecture |  | 100% | On Track
|  |  |  | Phase 3 Database Code |  | 100% | On Track
|  |  |  | QA Testing |  | 100% | On Track
|  |  |  | Group QA testing |  | 100% | On Track
|  |  |  | Demo 3 video |  | 100% | On Track
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
Team Meetings; Phase #3 Demo; Demo video; Class Readings; Database functions; QA manual testing; QA group testing; Group recording; Watching Buckaroo Banzai; Phase #3 coding and UI development; | [5 empty] | Graduate!
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Sam Wald | Project Manager | 7 | Risk
Logan Tailleur | Chief Architect | 8
Calvin Pugmire | Front-End Engineer | 7
Hunter Larson | QA Engineer | 4
Ethan Kerr | UI Designer | 3
Abel Nelson | Back-End Engineer | 7
Total |  | 36

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task